# Five-Year Environmental Sustainability Plan: Wigan Borough Federated Healthcare

Executive Summary

This Five-Year Environmental Sustainability Plan sets out how the Federation will contribute to the delivery of the Greater Manchester Integrated Care Board (ICB) Environmental Strategy, the NHS Net Zero ambition, and wider sustainability objectives across Greater Manchester.

As a provider of primary care services, the Federation recognises its responsibility to reduce environmental impact, improve population health, increase resilience to climate change, and support sustainable healthcare delivery. This plan outlines strategic priorities and actions for 2026–2031 under the key workplan headings identified by Greater Manchester ICB.

The plan supports:

- NHS Net Zero commitments (2040 and 2045 targets)

- NHS England Green Plan requirements

- Greater Manchester's ambition to become carbon neutral

- Improved health outcomes through sustainable healthcare

- Social value and environmental stewardship

Progress will be monitored annually through Quality and Governance Board meetings reporting to the Federation Board.

Vision

To become a leading sustainable primary care organisation that delivers high-quality healthcare while minimising environmental impact, improving resilience, and supporting healthier communities across Greater Manchester.

Strategic Objectives

By 2031, the Federation will:

- Reduce carbon emissions associated with its operations and services.

- Embed sustainability into clinical decision-making.

- Improve resilience to climate-related risks.

- Support sustainable travel and active lifestyles.

- Reduce waste and improve resource efficiency.

- Promote biodiversity and nature-based health interventions.

- Strengthen staff engagement and environmental leadership.

- Integrate sustainability into procurement and supply chains.

1. Workforce, Engagement and System Leadership

## Aim

Develop a workforce that understands, supports and champions environmental sustainability.

### Objectives

- Embed sustainability into organisational culture.

- Build environmental leadership capability.

- Engage staff, patients and partners in sustainability initiatives.

### Actions

| Year | Action |
| --- | --- |
| 2026 | Appoint Sustainability Lead, complete action plan & present to Board |
| 2026 | Include sustainability responsibilities within governance framework |
| 2027 | Deliver environmental awareness training for all staff |
| 2027 | Launch annual Green Staff Awards |
| 2028 | Embed sustainability into induction programmes |
| 2028 | Introduce sustainability objectives into leadership development programmes |
| 2029 | Develop patient engagement programme on sustainable healthcare |
| 2030 – 2031 | Participate in GM-wide sustainability networks and collaborative projects |

### Key Performance Indicators

- Sustainability Lead appointed.

- 90% of staff complete sustainability training.

- Annual staff engagement survey includes sustainability measures.

- Annual sustainability report produced.

2. Net Zero Clinical Transformation

Aim

Reduce emissions associated with clinical care while maintaining high-quality patient outcomes.

Objectives

- Embed sustainable clinical practice.

- Reduce unnecessary activity and waste.

- Promote prevention and self-management.

Actions 2026 – 2031:

| Year | Action |
| --- | --- |
| 2026 | Baseline carbon impact of Federation services |
| 2026 - 2027 | Promote personalised care and prevention programmes |
| 2027 | Introduce sustainable clinical pathways across Federation services |
| 2027 – 2028 | Support shared decision-making to reduce low-value interventions |
| 2028 | Develop sustainable models for long-term condition management |
| 2029 | Implement carbon considerations within service redesign processes |
| 2030 – 2031 | Evaluate and expand low-carbon care pathways |

### KPIs:

- Reduction in avoidable appointments.

- Increased uptake of prevention programmes.

- Sustainable clinical pathways implemented across priority services.

- Annual carbon reduction demonstrated.

3. Climate Change Adaptation

Aim

Improve resilience to the impacts of climate change.

Objectives

- Prepare for extreme weather events.

- Protect vulnerable patients.

- Ensure continuity of services.

Actions 2026 – 2031:

| Year | Action |
| --- | --- |
| 2026 | Undertake climate risk assessment |
| 2026 | Review business continuity plans |
| 2027 | Develop heatwave, flooding and severe weather response plans |
| 2027– 2028 | Identify vulnerable patient groups requiring targeted support |
| 2028 | Conduct annual resilience exercises |
| 2029 | Strengthen emergency preparedness with partner organisations |
| 2030 – 2031 | Review adaptation measures and update plans |

### KPIs

- Climate adaptation plan completed.

- Annual resilience exercises undertaken.

- Business continuity plans reviewed annually.

- Vulnerable patient register maintained.

4. Digital Transformation, Research and Innovation

Aim

Use digital solutions and innovation to reduce environmental impact and improve patient care.

Objectives

- Reduce travel and paper usage.

- Improve digital access.

- Support sustainable innovation.

Actions

| Year | Action |
| --- | --- |
| 2026 | Establish digital sustainability baseline |
| 2026 – 2027 | Increase digital consultations where clinically appropriate |
| 2027 | Move towards paper-light administration |
| 2028 | Introduce digital patient communications as default |
| 2028 – 2029 | Participate in sustainable healthcare research initiatives |
| 2029 | Pilot innovative low-carbon technologies |
| 2030 – 2031 | Evaluate and scale successful innovations |

### KPIs

- Reduction in paper consumption.

- Increase in digital communications.

- Number of innovation projects delivered.

- Reduction in patient travel emissions.

# 5. Travel, Transport and Air Quality

# Aim

Reduce travel-related emissions and improve air quality.

Objectives

- Encourage sustainable travel.

- Reduce fleet emissions.

- Promote active travel.

Actions

| Year | Action |
| --- | --- |
| 2026 | Complete staff travel survey |
| 2026 | Develop Sustainable Travel Policy |
| 2027 | Promote cycle-to-work schemes |
| 2027 | Improve bicycle storage facilities |
| 2028 | Increase use of virtual meetings |
| 2028 – 2029 | Support transition to electric vehicles where applicable |
| 2029 – 2031 | Participate in GM clean air initiatives |

### KPIs

- Staff travel emissions reduced by 20%.

- Increase in active travel uptake.

- Reduction in business mileage.

- Increased use of virtual meetings.

6. Estates and Facilities

Aim

Improve energy efficiency and reduce environmental impact from buildings.

Objectives

- Reduce energy consumption.

- Improve building performance.

- Increase resource efficiency.

Actions

| Year | Action |
| --- | --- |
| 2026 | Complete energy audits across Federation premises |
| 2026 -2027 | Implement low-cost energy efficiency measures |
| 2027 | Upgrade lighting to LED systems |
| 2028 | Introduce smart energy monitoring |
| 2028 -2029 | Assess opportunities for renewable energy |
| 2029 | Reduce water consumption through efficiency measures |
| 2030 -2031 | Review estate decarbonisation opportunities |

### KPIs

- Energy consumption reduced by 15%.

- Water consumption reduced by 10%.

- 100% LED lighting across Federation premises.

- Annual reduction in estate carbon emissions.

7. Medicines

Aim

Reduce environmental impacts associated with medicines while maintaining safe and effective prescribing.

Objectives

- Promote sustainable prescribing.

- Reduce medicine waste.

- Improve inhaler sustainability.

Actions 2026 – 2031:

| Year | Action |
| --- | --- |
| 2026 | Establish prescribing sustainability baseline |
| 2026 – 2027 | Promote structured medication reviews |
| 2027 | Reduce medicines waste through patient education |
| 2027 -2028 | Support lower-carbon inhaler prescribing where clinically appropriate |
| 2028 | Improve disposal and recycling awareness |
| 2029 - 2031 | Monitor prescribing carbon impacts and improve practice |

### KPIs

- Reduction in medicine waste.

- Increase in medication reviews completed.

- Increased uptake of lower-carbon inhalers where clinically appropriate.

- Annual prescribing sustainability review completed.

8. Supply Chain and Procurement

Aim:

Embed sustainability within procurement and commissioning activities.

Objectives:

- Purchase goods and services responsibly.

- Increase supplier engagement.

- Support local and sustainable economies.

Actions 2026 - 2031:

| Year | Action |
| --- | --- |
| 2026 | Review procurement processes |
| 2026–27 | Include sustainability criteria in procurement decisions |
| 2027 | Engage suppliers on net zero requirements |
| 2028 | Implement social value monitoring |
| 2028–29 | Prioritise local suppliers where appropriate |
| 2029 | Monitor supplier sustainability performance |
| 2030–31 | Embed environmental reporting requirements into contracts |

### KPIs

- Sustainability criteria included in procurement exercises.

- Increased supplier compliance with net zero requirements.

- Annual social value reporting completed.

9. Low Carbon Food

Aim

Promote healthier, lower-carbon food choices.

Objectives

- Reduce food-related emissions.

- Support healthy eating.

- Reduce food waste.

Actions

| Year | Action |
| --- | --- |
| 2026 | Review catering and hospitality arrangements |
| 2027 | Increase availability of plant-based options |
| 2027–28 | Introduce sustainable catering standards |
| 2028 | Reduce single-use packaging associated with catering |
| 2029 | Implement food waste reduction initiatives |
| 2030–31 | Review and strengthen sustainable food policies |

### KPIs

- Sustainable catering standards implemented.

- Food waste reduced annually.

- Increased uptake of plant-based food options.

10: Nature for Health

Aim

Improve health outcomes through connection with nature and biodiversity enhancement.

### Objectives

- Increase biodiversity.

- Support green social prescribing.

- Improve access to natural environments.

Actions 2026 – 2031:

| Year | Action |
| --- | --- |
| 2026 | Establish baseline assessment of green spaces |
| 2027 | Promote green social prescribing initiatives |
| 2027–28 | Introduce biodiversity improvements at Federation sites |
| 2028 | Work with local authorities and voluntary sector partners |
| 2029 | Support community environmental projects |
| 2030–31 | Expand nature-based health programmes |

### KPIs

- Increase in green social prescribing referrals.

- Biodiversity improvement projects delivered.

- Partnerships established with local environmental organisations.

- Positive patient outcomes reported

Governance and Reporting

The Federation Board will retain overall accountability for delivery of this plan.

### Governance Structure

- Federation Board

- Federation Quality Board

- Sustainability Lead

- Operational Leads

- GP Practice Representatives

### Monitoring

Progress will be reported annually against:

- Carbon emissions

- Energy consumption

- Travel emissions

- Sustainable prescribing metrics

- Procurement sustainability measures

- Workforce engagement indicators

- Nature and biodiversity outcomes

An annual Environmental Sustainability Report will be published and shared with Greater Manchester ICB and partner organisations.

Success Measures by 2031

- Sustainability embedded across all Federation services.

- Measurable reduction in organisational carbon emissions.

- Climate adaptation plans fully operational.

- Sustainable prescribing and medicines optimisation embedded.

- Improved active travel and reduced travel emissions.

- Enhanced biodiversity and nature-based health interventions.

- Staff actively engaged in environmental sustainability.

- Full alignment with Greater Manchester ICB environmental priorities and NHS Net Zero objectives